## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Initialize Database Schema & Knex Migrations | Create core normalized tables (users, roles, candidate_profiles, hr_profiles) and Knex migration framework | 1 | nhaphuong22/MockAI-Interview at main | Closed | PhuongLN | 2026-05-10 | 2026-05-12 | iter1 | Task, 3_Done | Database Schema Setup
Implement User Registration & Password Hashing | Build candidate/recruiter registration API with bcryptjs password hashing and role validation | 2 | nhaphuong22/MockAI-Interview at feature/auth | Closed | QuanNT | 2026-05-11 | 2026-05-14 | iter1 | Feature, 3_Done | Register
Implement JWT Login & Logout Session Handling | Develop JWT login authentication, Authorization bearer headers, and logout session destroy | 3 | nhaphuong22/MockAI-Interview at feature/auth | Closed | QuanNT | 2026-05-12 | 2026-05-15 | iter1 | Feature, 3_Done | Login / Logout
Integrate Google OAuth 2.0 Sign-In | Add Google OAuth 2.0 authentication flow allowing one-click candidate and recruiter login | 4 | nhaphuong22/MockAI-Interview at feature/oauth | Closed | QuanNT | 2026-05-15 | 2026-05-17 | iter1 | Feature, 3_Done | Login via Google
Build User Profile View & Edit UI | Create candidate & recruiter profile UI allowing edit personal details, avatar, and cover image | 5 | nhaphuong22/MockAI-Interview at feature/profile | Closed | HuyTG | 2026-05-16 | 2026-05-19 | iter1 | Feature, 3_Done | View & Edit Profile
Implement Password Change & Forgot Password Recovery | Add password change endpoint and Nodemailer OTP email link recovery for lost password | 6 | nhaphuong22/MockAI-Interview at feature/auth-recovery | Closed | PhuongLN | 2026-05-18 | 2026-05-21 | iter1 | Feature, 3_Done | Change & Forgot Password
Implement Admin User Management & Lock Account | Build Admin Users dashboard to inspect user list, toggle active/locked status, and assign roles | 7 | nhaphuong22/MockAI-Interview at feature/admin-users | Closed | SangPV | 2026-05-20 | 2026-05-24 | iter1 | Task, 3_Done | Manage Users
Build CV Upload, PDF Parsing & ATS Score Engine | Integrate pdf-parse to extract skills, experience, contact info from PDF resume and compute ATS score | 8 | nhaphuong22/MockAI-Interview at feature/cv-parser | Closed | HuyTG | 2026-05-26 | 2026-05-30 | iter2 | Feature, 3_Done | Upload & Parse CV
Export CV Feedback Review PDF Report | Generate formatted PDF report for CV evaluation and feedback recommendations using pdfkit | 9 | nhaphuong22/MockAI-Interview at feature/cv-export | Closed | HuyTG | 2026-06-01 | 2026-06-04 | iter2 | Feature, 3_Done | Export CV PDF Report
Build Job Posting Management for Recruiters | Develop recruiter job posting CRUD endpoints (POST /api/jobs), salary, requirements, and status toggle | 10 | nhaphuong22/MockAI-Interview at feature/job-management | Closed | TrieuND | 2026-06-03 | 2026-06-07 | iter2 | Feature, 3_Done | CRUD Job Postings
Implement Job Search & Company Grouping Filter | Candidate job search page with location, category, keyword filters, debounce, and company grouping | 11 | nhaphuong22/MockAI-Interview at feature/job-search | Closed | SangPV | 2026-06-08 | 2026-06-12 | iter2 | Feature, 3_Done | Search & Filter Jobs
Implement Candidate Application & Tracking Flow | Candidate job application submission with parsed CV selector and real-time application status tracking | 12 | nhaphuong22/MockAI-Interview at feature/apply-job | Closed | SangPV | 2026-06-10 | 2026-06-14 | iter2 | Feature, 3_Done | Apply for Job & Track Status
Build Company Profile Management & Followers | CompanyProfile view/edit mode with Markdown editor, banner, tax code validation, and candidate follow toggle | 13 | nhaphuong22/MockAI-Interview at feature/company-profile | Closed | TrieuND | 2026-06-12 | 2026-06-16 | iter2 | Feature, 3_Done | View & Follow Company
Integrate VNPay Sandbox Payment & Credit Packages | VNPay sandbox payment gateway integration for recruiters purchasing credit packages and invoice handling | 14 | nhaphuong22/MockAI-Interview at feature/vnpay-payment | Closed | QuanNT | 2026-06-15 | 2026-06-19 | iter2 | Feature, 3_Done | Buy Credit Packages via VNPay
Implement Employer VIP Packages & Coupon System | VIP company subscription package purchase for search priority and promotional coupon discount codes | 15 | nhaphuong22/MockAI-Interview at feature/vip-coupon | Closed | QuanNT | 2026-06-18 | 2026-06-22 | iter2 | Feature, 3_Done | VIP Package & Coupon Code
Build Admin Job Moderation & Auto-Hide Expired Posts | Admin job moderation page to approve/reject HR job postings, hide unapproved jobs, and auto-expire postings | 16 | nhaphuong22/MockAI-Interview at feature/admin-job-moderation | Closed | SangPV | 2026-06-20 | 2026-06-24 | iter2 | Task, 3_Done | Moderate Job Posts
Render 3D Virtual AI Avatar & Audio/Video Prep Room | Build 3D WebGL avatar room using Three.js/R3F, mic/webcam device test modal, and candidate badge | 17 | nhaphuong22/MockAI-Interview at feature/3d-ai-interview | Closed | PhuongLN | 2026-06-25 | 2026-06-29 | iter3 | Feature, 3_Done | 3D AI Interview Setup
Implement Real-time AI Voice Dialogue Engine | Develop voice interview room with Whisper STT audio recorder, real-time AI response streaming & TTS speech | 18 | nhaphuong22/MockAI-Interview at feature/ai-voice-engine | Closed | PhuongLN | 2026-06-28 | 2026-07-02 | iter3 | Feature, 3_Done | AI Voice Interview Room
Build Adaptive AI Context-Aware Question Generator | Prompt AI engine to generate custom interview questions dynamically from Candidate CV and Job Description | 19 | nhaphuong22/MockAI-Interview at feature/ai-question-generator | Closed | PhuongLN | 2026-07-01 | 2026-07-05 | iter3 | Feature, 3_Done | AI Question Generator
Develop AI Evaluation Scoring & Radar Chart Report | Generate detailed AI interview scoring report with constructive feedback and 5-axis Radar Chart competency metrics | 20 | nhaphuong22/MockAI-Interview at feature/ai-report-radarchart | Closed | PhuongLN | 2026-07-04 | 2026-07-08 | iter3 | Feature, 3_Done | AI Assessment & Radar Chart
Implement Anti-Cheat Gaze Detection & Tab Monitor | Use MediaPipe gaze tracking for eye deviation & tab switch detection; trigger warning banner & penalty points | 21 | nhaphuong22/MockAI-Interview at feature/anti-cheat-gaze | Closed | PhuongLN | 2026-07-06 | 2026-07-10 | iter3 | Security, 3_Done | Anti-Cheat Gaze & Tab Monitor
Implement Candidate / HR Auth Role Switcher Modal | Seamless role selection and auto-switching modal inside login flow without token expiration or relogin | 22 | nhaphuong22/MockAI-Interview at feature/auth-role-switch | Closed | QuanNT | 2026-07-08 | 2026-07-12 | iter3 | Feature, 3_Done | Auth Role Switcher
Build Socket.io Real-time HR-Candidate Messaging | Real-time chat room using Socket.io between recruiters and candidates with online status indicators | 23 | nhaphuong22/MockAI-Interview at feature/socket-chat | Closed | PhuongLN | 2026-07-10 | 2026-07-14 | iter3 | Feature, 3_Done | Realtime Messaging
Implement Violation Report Modal & Submission API | Add ReportModal component across Jobs, Blogs, and User profiles to let users submit content violation reports | 24 | nhaphuong22/MockAI-Interview at feature/report-violation | Closed | TrieuND | 2026-07-12 | 2026-07-15 | iter3 | Feature, 3_Done | Report Violation
Build Admin Moderate Reports & Soft-Delete Content | Admin Manage Reports page with ReportDetailModal, soft-delete toggle (REJECTED status / is_warned banner), and unhide API | 25 | nhaphuong22/MockAI-Interview at feature/admin-reports-moderation | Closed | TrieuND | 2026-07-14 | 2026-07-17 | iter3 | Task, 3_Done | Manage Violation Reports
Implement Custom Email Notifications for HR Status | Send automated custom email notifications to candidates via Nodemailer when HR updates application status | 26 | nhaphuong22/MockAI-Interview at feature/email-notifications | Closed | TrieuND | 2026-07-16 | 2026-07-18 | iter3 | Feature, 3_Done | Email Notifications
Build Community Blog System with Markdown Editor | Community Blog Feed with WriteBlogModal, Markdown live editor, cover photo upload, tag filtering & grid card layout | 27 | nhaphuong22/MockAI-Interview at feature/community-blog | Closed | HuyTG | 2026-07-17 | 2026-07-19 | iter3 | Feature, 3_Done | Community Blog & Write Blog
Build Master Admin Analytics Dashboard & System Metrics | Master Admin Dashboard displaying real database analytics for users, active jobs, AI interviews, and revenue | 28 | nhaphuong22/MockAI-Interview at feature/admin-analytics | Closed | SangPV | 2026-07-18 | 2026-07-20 | iter3 | Task, 3_Done | Admin Dashboard Analytics