## Project
Total Project Tracking
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Register (Đăng ký tài khoản) | Authentication & Authorization | User / Guest | Register new account to access platform features (Candidate or Recruiter role) | Nguyễn Tam Quân | Done | iter1
2 | Login / Logout (Đăng nhập / Đăng xuất) | Authentication & Authorization | User | Access platform via credentials and handle JWT session termination | Nguyễn Tam Quân | Done | iter1 | iter3 | Integrated role switcher and socket auto-reconnection
3 | Login via Google (Đăng nhập Google) | Authentication & Authorization | User | One-click OAuth 2.0 authentication using Google Account credentials | Nguyễn Tam Quân | Done | iter1
4 | View & Edit Profile (Hồ sơ cá nhân) | User Management & Profile | Candidate / Recruiter | View and edit personal info, avatar image, and persistent cover photo | Trần Gia Huy | Done | iter1 | iter3 | Added cover photo persistence and redesigned profile layout
5 | Change & Forgot Password (Đổi & Quên MK) | Authentication & Security | User | Password change validation and OTP-based email password recovery flow | Lê Nhã Phương | Done | iter1
6 | Database Schema & Migrations (Cấu trúc CSDL) | System Architecture | Developer / Admin | Initialize normalized PostgreSQL Knex migrations, tables, indexes and constraints | Lê Nhã Phương | Done | iter1 | iter2 | Added company profile, payment, coupon, and report schema
7 | Manage Users & Lock Account (Quản lý User) | Admin Governance | Admin | View user accounts list, assign RBAC permissions matrix, toggle active/locked status | Phạm Văn Sang | Done | iter1 | iter3 | Integrated RBAC permissions matrix UI controls
8 | Upload & Parse CV (Tải & Phân tích CV) | CV Management & ATS | Candidate | Upload PDF resume, extract contact info, skills, and compute initial ATS score | Trần Gia Huy | Done | iter2 | iter3 | Added pdf-parse error handling and candidate info extraction
9 | Export CV Review PDF Report (Xuất PDF CV) | CV Management & ATS | Candidate | Export formatted PDF report for CV feedback using pdfkit engine | Trần Gia Huy | Done | iter2
10 | Post & Manage Jobs (Đăng & Quản lý tin) | Recruitment & Job Portal | Recruiter | HR creates, updates, closes job postings with requirements, salary, and credits | Nguyễn Đông Triều | Done | iter2 | iter3 | Added credit deduction check and auto-expire status
11 | Search & Filter Jobs (Tìm & Lọc công việc) | Candidate Job Portal | Candidate / Guest | Search job posts by keyword, location, and group listings by company with debounce filter | Phạm Văn Sang | Done | iter2
12 | Apply for Job & Track Status (Ứng tuyển) | Candidate Job Portal | Candidate | Candidates apply for jobs with parsed CV and monitor hiring progress in real-time | Phạm Văn Sang | Done | iter2 | iter3 | Added real-time error messages for phone and email validation
13 | View & Follow Company (Xem & Theo dõi CT) | Company Management | Candidate / Recruiter | Candidates follow target companies; HR updates company profile, banner, and tax code | Nguyễn Đông Triều | Done | iter2 | iter3 | Added View/Edit mode, Markdown editor, and followers list
14 | Buy Credit Packages via VNPay (Thanh toán) | Wallet & Payments | Recruiter | Employers purchase credit packages via VNPay sandbox payment gateway | Nguyễn Tam Quân | Done | iter2
15 | VIP Packages & Coupon System (Gói VIP & Coupon) | Wallet & Payments | Recruiter | Purchase VIP company badge for priority placement; apply promotional coupons | Nguyễn Tam Quân | Done | iter2 | iter3 | Enhanced landing page UI, coupon list, and VIP company sorting
16 | Moderate Job Posts (Kiểm duyệt tin tuyển dụng) | Admin Governance | Admin | Admin approves/rejects HR job postings; auto-hides expired job postings | Phạm Văn Sang | Done | iter2 | iter3 | Restricted unapproved job visibility and secured API access
17 | 3D AI Interview Setup (Phòng phỏng vấn 3D) | AI Virtual Interview | Candidate | Check audio input/webcam, render 3D WebGL avatar model in interview setup | Lê Nhã Phương | Done | iter3
18 | Conduct AI Voice Interview Room (Phỏng vấn thoại) | AI Virtual Interview | Candidate | Real-time interactive voice dialogue with AI avatar using Whisper STT & TTS speech | Lê Nhã Phương | Done | iter3
19 | Adaptive AI Question Generator (AI sinh câu hỏi) | AI Virtual Interview | Candidate / HR | Context-aware AI engine generates custom interview questions from CV and JD context | Lê Nhã Phương | Done | iter3
20 | AI Assessment & Radar Chart (Báo cáo AI) | AI Virtual Interview | Candidate / HR | Evaluate candidate responses with detailed feedback and 5-axis Radar Chart metrics | Lê Nhã Phương | Done | iter3
21 | Anti-Cheat Detection (Gaze & Tab Monitor) | AI Virtual Interview & Security | Candidate | Monitor webcam gaze deviation and browser tab switching; log penalty points | Lê Nhã Phương | Done | iter3
22 | Auth Role Switcher (Chuyển vai trò Candidate/HR) | Authentication & UX | User | Switch role between Candidate and HR seamlessly inside login modal without relogin | Nguyễn Tam Quân | Done | iter3
23 | Realtime Messaging (Nhắn tin thời gian thực) | Recruitment & Realtime | Candidate / Recruiter | Socket.io real-time chat between candidate and HR recruiter with online status | Lê Nhã Phương | Done | iter3
24 | Report Violation Modal (Báo cáo vi phạm) | Community & Security | Candidate / Recruiter | Users submit violation reports for inappropriate jobs, blogs, or user profiles | Nguyễn Đông Triều | Done | iter3
25 | Admin Moderate Reports (Kiểm duyệt báo cáo) | Admin Governance | Admin | Admin reviews reports, soft-deletes/hides reported content, and notifies author | Nguyễn Đông Triều | Done | iter3
26 | Custom Email Notifications (Email tự động) | Recruitment System | Recruiter / Candidate | Automatic email notification via Nodemailer when HR updates application status | Nguyễn Đông Triều | Done | iter3
27 | Community Blog & Write Blog (Blog cộng đồng) | Community Engagement | Candidate | Write blog articles with Markdown editor, cover photo, category tags, and grid feed | Trần Gia Huy | Done | iter3
28 | Admin Master Dashboard (Thống kê hệ thống) | Admin Governance | Admin | Display real database analytics for users, active jobs, AI interviews, and revenue | Phạm Văn Sang | Done | iter3
Effort Distribution
No | Full name | Student ID | Effort (%)
1 | Lê Nhã Phương | DE20A02 | 30%
2 | Nguyễn Tam Quân |  | 18%
3 | Nguyễn Đông Triều |  | 18%
4 | Phạm Văn Sang |  | 17%
5 | Trần Gia Huy |  | 17%

## Iter1
Iteration Tracking - Iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Register | Authentication & Authorization | Register new account to access platform features (Candidate or Recruiter role) | Nguyễn Tam Quân | Done | UC-01 | 2.1
2 | Login / Logout | Authentication & Authorization | Access platform via credentials and handle JWT session termination | Nguyễn Tam Quân | Done | UC-02 | 2.2
3 | Login via Google | Authentication & Authorization | One-click OAuth 2.0 authentication using Google Account credentials | Nguyễn Tam Quân | Done | UC-02 | 2.2
4 | View & Edit Profile | User Management & Profile | View and edit personal info, avatar image, and persistent cover photo | Trần Gia Huy | Done | UC-06 | 2.6
5 | Change & Forgot Password | Authentication & Security | Password change validation and OTP-based email password recovery flow | Lê Nhã Phương | Done | UC-04 | 2.4
6 | Database Schema Setup | System Architecture | Initialize normalized PostgreSQL Knex migrations, tables, indexes and constraints | Lê Nhã Phương | Done | UC-57 | 10.10
7 | Manage Users | Admin Governance | View user accounts list, assign RBAC permissions matrix, toggle active/locked status | Phạm Văn Sang | Done | UC-49 | 10.2

## Iter2
Iteration Tracking - Iteration 2
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Upload & Parse CV | CV Management & ATS | Upload PDF resume, extract contact info, skills, and compute initial ATS score | Trần Gia Huy | Done | UC-10 | 3.1
2 | Export CV PDF Report | CV Management & ATS | Export formatted PDF report for CV feedback using pdfkit engine | Trần Gia Huy | Done | UC-10 | 3.1
3 | CRUD Job Postings | Recruitment & Job Portal | HR creates, updates, closes job postings with requirements, salary, and credits | Nguyễn Đông Triều | Done | UC-28 | 6.4
4 | Search & Filter Jobs | Candidate Job Portal | Search job posts by keyword, location, and group listings by company with debounce filter | Phạm Văn Sang | Done | UC-14 | 4.2
5 | Apply for Job & Track Status | Candidate Job Portal | Candidates apply for jobs with parsed CV and monitor hiring progress in real-time | Phạm Văn Sang | Done | UC-16 | 4.4
6 | View & Follow Company | Company Management | Candidates follow target companies; HR updates company profile, banner, and tax code | Nguyễn Đông Triều | Done | UC-19 | 4.7
7 | Buy Credit Packages via VNPay | Wallet & Payments | Employers purchase credit packages via VNPay sandbox payment gateway | Nguyễn Tam Quân | Done | UC-36 | 7.1
8 | VIP Package & Coupon Code | Wallet & Payments | Purchase VIP company badge for priority placement; apply promotional coupons | Nguyễn Tam Quân | Done | UC-36 | 7.1
9 | Moderate Job Posts | Admin Governance | Admin approves/rejects HR job postings; auto-hides expired job postings | Phạm Văn Sang | Done | UC-51 | 10.4

## Iter3
Iteration Tracking - Iteration 3
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | 3D AI Interview Setup | AI Virtual Interview | Check audio input/webcam, render 3D WebGL avatar model in interview setup | Lê Nhã Phương | Done | UC-21 | 5.2
2 | AI Voice Interview Room | AI Virtual Interview | Real-time interactive voice dialogue with AI avatar using Whisper STT & TTS speech | Lê Nhã Phương | Done | UC-22 | 5.3
3 | AI Question Generator | AI Virtual Interview | Context-aware AI engine generates custom interview questions from CV and JD context | Lê Nhã Phương | Done | UC-20 | 5.1
4 | AI Assessment & Radar Chart | AI Virtual Interview | Evaluate candidate responses with detailed feedback and 5-axis Radar Chart metrics | Lê Nhã Phương | Done | UC-23 | 5.4
5 | Anti-Cheat Gaze & Tab Monitor | AI Virtual Interview & Security | Monitor webcam gaze deviation and browser tab switching; log penalty points | Lê Nhã Phương | Done | UC-22 | 5.3
6 | Auth Role Switcher | Authentication & UX | Switch role between Candidate and HR seamlessly inside login modal without relogin | Nguyễn Tam Quân | Done | UC-02 | 2.2
7 | Realtime Messaging | Recruitment & Realtime | Socket.io real-time chat between candidate and HR recruiter with online status | Lê Nhã Phương | Done | UC-31 | 6.7
8 | Report Violation | Community & Security | Users submit violation reports for inappropriate jobs, blogs, or user profiles | Nguyễn Đông Triều | Done | UC-47 | 9.3
9 | Manage Violation Reports | Admin Governance | Admin reviews reports, soft-deletes/hides reported content, and notifies author | Nguyễn Đông Triều | Done | UC-53 | 10.6
10 | Email Notifications | Recruitment System | Automatic email notification via Nodemailer when HR updates application status | Nguyễn Đông Triều | Done | UC-35 | 6.11
11 | Community Blog & Write Blog | Community Engagement | Write blog articles with Markdown editor, cover photo, category tags, and grid feed | Trần Gia Huy | Done | UC-40 | 8.1
12 | Admin Dashboard Analytics | Admin Governance | Display real database analytics for users, active jobs, AI interviews, and revenue | Phạm Văn Sang | Done | UC-48 | 10.1